## Test Cases
Product Name |  | Evaly | TC Start Date | 2020-08-07 | TC Execution Start Date | 2020-08-07 | TEST CASE SUMMARY
Module Name |  | Test Cases for Registration process | TC End Date | 2020-08-07 | TC Execution End Date | 2020-08-07 | PASS | 9
|  |  | Test Case Developed By | IMRAN AL MUNYEEM | Browser (tested) | Yes | FAIL | 6
Developer Name (TL) |  |  | Test Case Reviewed By | Md. Sabiul Islam | Performance (tested) | No | WARNING | 0
Test Executed by | [6 empty] | TOTAL | 15
Test Case ID/Name | Test Case Description | Step Name | Test Data | Step Description | Expected Result | Actual | Status | Remarks
TC001 | Registration with Phone Number | Step 1 |  | Click on the "Next" Button | Should not be able to register with blank phone number | Not able to register | PASS
TC002 | Registration with Phone Number | Step 1 | 01633373088 | Click on the "Next" Button | Should be able to register with valid phone number | Able to register | PASS | Valid phone number
|  | Step 2 |  | Using valid Phone Number
TC003 | Registration with Phone Number | Step 1 | dfdfdfdfdfd | Click on the "Next" Button | Should not be able to register with invalid phone number | Not able to register | PASS | Invalid phone number
|  | Step 2 |  | Using invalid Phone Number
TC004 | Registration with Phone Number | Step 1 | 88888999994 | Click on the "Next" Button | Should not be able to register with invalid phone number | Able to register | FAIL | Log in with invalid phn num1
|  | Step 2 |  | Invalid Phone number
TC005 | Registration with Phone Number | Step 1 | 88888999997 | Click on the "Next" Button | Should not be able to register with invalid phone number | Able to register
|  | Step 2 |  | Used but not registered with OTP | Should sent OTP again | Show pop up as "Already used number" | FAIL | Log in with invalid phn num2
TC006 | Registration with First name | Step 1 |  | Click on the "Next" Button | Should not be able to register with blank first name | Able to register | PASS | Blank first name
|  | Step 2 |  | Using blank input
TC007 | Registration with First name | Step 1 | Suparna | Click on the "Next" Button | Should be able to register with valid first name | Able to register | PASS | Valid first name
|  | Step 2 |  | Using valid First name
TC008 | Registration with First name | Step 1 | ;;;;; | Click on the "Next" Button | Should be able to register with invalid first name | Able to register | FAIL | Login with invalid first name1
|  | Step 2 |  | Using invalid First name
TC009 | Registration with First name | Step 1 | 8989 | Click on the "Next" Button | Should be able to register with invalid first name | Able to register | FAIL | Login with invalid first name2
|  | Step 2 |  | Using invalid First name
TC010 | Registration with last name | Step 1 |  | Click on the "Next" Button | Should not be able to register with blank first name | Not able to register | PASS | Blank last name
|  | Step 2 |  | Using blank input
TC011 | Registration with last name | Step 1 | Shil | Click on the "Next" Button | Should be able to register with valid password | Able to register | PASS | Login with valid last name
|  | Step 2 |  | Using valid Last name
TC012 | Registration with last name | Step 1 | ();"*>? | Click on the "Next" Button | Should not be able to register with invalid last name | Able to register | FAIL | Login with invalid last name1
|  | Step 2 |  | Using invalid Last name
TC013 | Registration with last name | Step 1 | 8989 | Click on the "Next" Button | Should not be able to register with invalid last name | Able to register | FAIL | Login with invalid last name1
|  | Step 2 |  | Using invalid Last name
TC014 | Registration with password | Step 1 | 123456 | Click on the "Next" Button | Should not be able to register without 8 length password with atleast 1 special character | Not able to register | PASS | Weak password
|  | Step 2 |  | Using 6 length weak password
TC015 | Registration with password | Step 1 | abcd1234+? | Click on the "Next" Button | Should be able to register without 8 length password with atleast 1 special character | Able to register | PASS | Login with strong password
|  | Step 2 |  | Using 8 length password with atleast 1 special character